## 🛠 Master Checklist
NeuroQuest Zen Pro — Developer Sprint Checklist
Whitney Ausbrooks, Founder/CEO ¦ NeuroQuest LLC ¦ admin@neuroquestllc.info ¦ neuroquestllc.info ⚠️ Backend / Auth / Data / Wearables / Audio ONLY — No UI changes
# | Task / Requirement | Technical Detail | Priority | Status | Owner | Notes / ETA
🔐 1. AUTHENTICATION
1.1 | Implement persistent auth tokens | JWT or session tokens; store in DB with expiry | 🔴 Critical | ⬜ Not Started
1.2 | Secure local token storage | iOS: Keychain ¦ Android: Keystore | 🔴 Critical | ⬜ Not Started
1.3 | Silent background token refresh | Refresh before expiry; no user prompt | 🔴 Critical | ⬜ Not Started
1.4 | Add Logout Button (UI exception) | Visible on Home / Profile screen; clears token + local cache | 🔴 Critical | ⬜ Not Started
1.5 | Session timeout handling | Auto-logout after X mins idle; configurable in admin | 🟡 High | ⬜ Not Started
1.6 | Multi-device session management | Track active sessions per user in DB | 🟡 High | ⬜ Not Started
1.7 | Auth event logging | Log login / logout / token refresh with timestamp + device | 🟡 High | ⬜ Not Started
🗄️ 2. DATABASE & DATA STORAGE
2.1 | HRV readings schema | user_id, timestamp, device_source, hrv_ms, quality_flag | 🔴 Critical | ⬜ Not Started
2.2 | Sleep score schema | user_id, date, total_sleep_min, deep_min, rem_min, score | 🔴 Critical | ⬜ Not Started
2.3 | Strain / activity schema | user_id, timestamp, strain_score, calories, steps | 🔴 Critical | ⬜ Not Started
2.4 | Neuro-Resilience Score history | Persist every score calculation with inputs snapshot | 🔴 Critical | ⬜ Not Started
2.5 | Burnout risk flag table | Threshold triggers, timestamp, severity level, resolved_at | 🔴 Critical | ⬜ Not Started
2.6 | Session log table | session_id, user_id, start/end, protocol_id, completion % | 🟡 High | ⬜ Not Started
2.7 | AI input/output log | Log every model call: inputs, recommendation, timestamp | 🟡 High | ⬜ Not Started
2.8 | Outcome feedback table | AI recommendation → user action → next HRV/sleep delta | 🟡 High | ⬜ Not Started
2.9 | Wearable sync log | device_type, sync_time, records_received, errors | 🟡 High | ⬜ Not Started
2.10 | Data retention policy | Define TTL per data type; archive vs delete strategy | 🟢 Medium | ⬜ Not Started
2.11 | Database backups | Automated daily backups; test restore quarterly | 🟢 Medium | ⬜ Not Started
⌚ 3. WEARABLE INTEGRATIONS
3.1 | Apple Watch — HealthKit | HRV, sleep, heart rate, activity; background delivery ON | 🔴 Critical | ⬜ Not Started
3.2 | Samsung Galaxy Watch — Health Connect | Use Health Connect Android API; request all permissions | 🔴 Critical | ⬜ Not Started
3.3 | Garmin — Health Connect / Connect IQ | Primary: Health Connect fallback; secondary: Connect IQ SDK | 🟡 High | ⬜ Not Started
3.4 | Fitbit — Fitbit Web API | OAuth 2.0; HRV (premium), sleep, heart rate | 🟡 High | ⬜ Not Started
3.5 | Whoop — WHOOP API | Strain, recovery, sleep; webhook for real-time push | 🟡 High | ⬜ Not Started
3.6 | Polar — Open AccessLink API | HRV, training load, sleep; OAuth 2.0 | 🟢 Medium | ⬜ Not Started
3.7 | Off-brand / generic — Health Connect | Android Health Connect as universal fallback | 🟡 High | ⬜ Not Started
3.8 | Unified data normalizer | Map all device outputs → standard internal schema | 🔴 Critical | ⬜ Not Started
3.9 | Device source label on every record | Tag each DB row with device_source string | 🔴 Critical | ⬜ Not Started
3.10 | Wearable connection status dashboard | Admin view: which devices synced, last sync time, errors | 🟡 High | ⬜ Not Started
3.11 | Handle missing / partial data | Graceful fallback when wearable data is incomplete | 🟡 High | ⬜ Not Started
🤖 4. AI LEARNING LOOP
4.1 | Tag all stored data for ML retrieval | Add is_training_eligible flag + feature vector on write | 🔴 Critical | ⬜ Not Started
4.2 | AI recommendation logging | Store rec_type, confidence, model_version, user_id, ts | 🔴 Critical | ⬜ Not Started
4.3 | Outcome feedback write on every session | Compare pre/post biometrics; write delta to feedback table | 🔴 Critical | ⬜ Not Started
4.4 | Model retraining pipeline | Scheduled job to retrain on new feedback data | 🟡 High | ⬜ Not Started
4.5 | Model versioning | Track which model version made each recommendation | 🟡 High | ⬜ Not Started
4.6 | Anomaly detection logging | Flag and store unusual biometric readings for review | 🟢 Medium | ⬜ Not Started
4.7 | A/B test framework | Compare protocol variants; log which version each user saw | 🟢 Medium | ⬜ Not Started
🎵 5. BINAURAL BEATS
5.1 | Verify stereo output — NOT mono | Critical for binaural effect; test on device, not simulator | 🔴 Critical | ⬜ Not Started
5.2 | Focus track loads & plays correctly | Confirm correct Hz file, no truncation, smooth loop | 🔴 Critical | ⬜ Not Started
5.3 | Recovery track loads & plays correctly | Same as above for recovery session type | 🔴 Critical | ⬜ Not Started
5.4 | Sleep track loads & plays correctly | Same as above for sleep session type | 🔴 Critical | ⬜ Not Started
5.5 | Session audio logging | Log track_id, duration_played, session_id to DB | 🟡 High | ⬜ Not Started
5.6 | Audio interruption handling | Resume correctly after call, notification, or focus change | 🟡 High | ⬜ Not Started
5.7 | Volume normalization | All tracks consistent volume; no clipping | 🟢 Medium | ⬜ Not Started
5.8 | Offline audio playback | Audio files bundled locally; no stream-fail on no network | 🟢 Medium | ⬜ Not Started
📊 6. LIVE DASHBOARDS
6.1 | All dashboards read from live DB | No hardcoded / mock / cached data in production | 🔴 Critical | ⬜ Not Started
6.2 | Real-time refresh (WebSocket or polling) | Define refresh interval; confirm data updates without reload | 🔴 Critical | ⬜ Not Started
6.3 | HR burnout risk panel — live | Pulls current burnout flags from DB in real time | 🔴 Critical | ⬜ Not Started
6.4 | Neuro-Resilience Score dashboard — live | Trend chart from score history table | 🟡 High | ⬜ Not Started
6.5 | ROI metrics dashboard — live | Calculates from session + outcome data; no stale cache | 🟡 High | ⬜ Not Started
6.6 | Wearable sync status panel | Shows device, last sync, data received count | 🟡 High | ⬜ Not Started
6.7 | Error / alert log panel | Surface DB write errors, sync failures, auth errors | 🟡 High | ⬜ Not Started
6.8 | Dashboard access auth | Dashboards protected by role-based auth (admin vs HR vs exec) | 🔴 Critical | ⬜ Not Started
🔒 7. SECURITY & COMPLIANCE
7.1 | All data encrypted at rest | AES-256 or equivalent for DB storage | 🔴 Critical | ⬜ Not Started
7.2 | All data encrypted in transit | TLS 1.2+ on all API endpoints | 🔴 Critical | ⬜ Not Started
7.3 | HIPAA-pathway data handling | PHI fields identified, access logged, minimum necessary rule | 🟡 High | ⬜ Not Started
7.4 | SOC 2 audit trail | Log all data access events with user, action, timestamp | 🟡 High | ⬜ Not Started
7.5 | API rate limiting | Prevent abuse on all endpoints; return 429 with retry-after | 🟡 High | ⬜ Not Started
7.6 | Input sanitization | Validate + sanitize all user/device inputs before DB write | 🔴 Critical | ⬜ Not Started
7.7 | Secret / key management | No secrets in code; use env vars or secrets manager | 🔴 Critical | ⬜ Not Started
✅ 8. QA & SIGN-OFF
8.1 | End-to-end auth flow test | Login → use app → close → reopen → still logged in | 🔴 Critical | ⬜ Not Started
8.2 | Logout button test | Tap logout → token cleared → redirect to login | 🔴 Critical | ⬜ Not Started
8.3 | Wearable sync test (each device) | Sync each brand; verify data appears in DB correctly | 🔴 Critical | ⬜ Not Started
8.4 | Binaural stereo test on device | Use headphones on real device; confirm L/R channel split | 🔴 Critical | ⬜ Not Started
8.5 | Dashboard live-data test | Change a biometric → confirm dashboard updates within interval | 🔴 Critical | ⬜ Not Started
8.6 | AI log verification | Complete session → verify AI log + feedback row in DB | 🟡 High | ⬜ Not Started
8.7 | Load / stress test | Simulate 100 concurrent users; check DB write throughput | 🟢 Medium | ⬜ Not Started
8.8 | Security penetration test | Run OWASP ZAP or similar; fix all high/critical findings | 🟡 High | ⬜ Not Started

## ⚠️ Gaps & Additions
NeuroQuest Zen Pro — Gaps & Items Not in Original Brief
# | Gap / Missing Item | Why It Matters | Priority | Action Required
G1 | Logout Button | Users have no way to sign out — auth tokens never clear; security risk | 🔴 Critical | Add visible logout button on Home/Profile; clear token + local cache on tap
G2 | Session timeout / auto-logout | Without it, stolen devices stay permanently logged in | 🔴 Critical | Set idle timeout (e.g., 30 min); configurable per org in enterprise settings
G3 | Multi-device session tracking | Users may log in on phone + tablet; no visibility into active sessions | 🟡 High | Track sessions in DB; allow user to revoke other sessions
G4 | Role-based access control (RBAC) | HR, C-suite, and admin need different dashboard views | 🔴 Critical | Define roles; restrict dashboard routes by role in auth layer
G5 | Data encryption at rest | Biometric data is PHI — unencrypted DB is a compliance blocker | 🔴 Critical | Enable AES-256 encryption on DB; document for SOC 2 / HIPAA audit
G6 | HIPAA minimum-necessary rule | All PHI access must be logged; only necessary fields exposed | 🟡 High | Audit DB queries; add access log table; mask PHI in non-essential views
G7 | API rate limiting | No throttle = vulnerable to abuse / data scraping | 🟡 High | Add rate limiting middleware on all API routes; return 429 with retry-after
G8 | Input sanitization | Unsanitized wearable/user inputs can corrupt DB or enable injection | 🔴 Critical | Validate + sanitize all inputs before DB write; use parameterized queries
G9 | Secret / key management | API keys in code = major security risk | 🔴 Critical | Move all secrets to env vars or AWS Secrets Manager / equivalent
G10 | Database backup strategy | No backup plan = total data loss risk on DB failure | 🔴 Critical | Set up automated daily backups; test restore process before launch
G11 | Model versioning for AI | Can't diagnose AI errors without knowing which model made each rec | 🟡 High | Tag every AI output with model_version; store in AI log table
G12 | Wearable sync error handling | If Garmin/Fitbit API fails, what happens? Silent failure = bad data | 🟡 High | Catch API errors; log to sync_errors table; surface in admin dashboard
G13 | Offline mode / data queue | Users in poor connectivity lose session data permanently | 🟡 High | Queue data locally; sync to DB when connection restores
G14 | Audio interruption handling | Phone call mid-session = binaural track stops; no resume logic | 🟡 High | Handle audio session interruptions; resume or restart track gracefully
G15 | Notification / alert system | Burnout risk flags have no delivery mechanism to HR | 🟡 High | Add push/email alert pipeline for threshold triggers to HR dashboard
G16 | SCIM 2.0 enterprise provisioning | Required for enterprise SSO / user management (in your pitch deck) | 🟡 High | Implement SCIM 2.0 endpoints for enterprise customer onboarding
G17 | Crash / error monitoring | No visibility into production errors without a monitoring tool | 🟡 High | Integrate Sentry or equivalent; alert on critical errors in real time
G18 | Analytics event tracking | No data on how users move through app = blind product decisions | 🟢 Medium | Add event tracking (Mixpanel / Amplitude / custom); log key user actions
G19 | Terms of Service / Privacy Policy acceptance | Required for HIPAA and App Store compliance | 🔴 Critical | Force acceptance on first login; log acceptance timestamp + version to DB
G20 | App Store compliance — HealthKit disclosure | Apple requires explicit HealthKit usage description strings | 🔴 Critical | Add all required NSHealthKit* usage description keys to Info.plist

## 📋 Ground Rules
NeuroQuest Zen Pro — Developer Ground Rules
🚫 NO UI Changes
Do not change any screen layout, colors, copy, fonts, or user-facing design. This sprint is backend + infrastructure only.
✅ Confirm Before Closing Each Section
Every section in the Master Checklist must be marked ✅ Complete before the sprint is closed. No partial sign-offs.
🔐 Auth First
Auth (persistent login + logout button) must be the first thing completed and tested.
📦 Every Write Goes to the DB
No data should exist only in memory or local state. Every biometric reading, session, AI recommendation, and auth event writes to the database.
🏷 Tag Every Record
Every DB record must include: user_id, timestamp, device_source, and data_type. No exceptions.
🎵 Test Audio on Real Device
Binaural beats MUST be tested on a physical device with headphones — not in a simulator. Stereo output is required.
📊 No Mock Data in Production
All dashboards must read from live database queries. Remove all hardcoded/mock data before handoff.
🔒 No Secrets in Code
API keys, tokens, and credentials belong in environment variables or a secrets manager — never in source code or version control.
📝 Document Everything
Leave inline comments for any non-obvious logic. Update README with new env vars, DB schema changes, and API integrations added this sprint.
⚠️ Report Blockers Immediately
If any integration (Garmin, Whoop, etc.) is blocked by API access, report within 24 hours so Whitney can request credentials.